## Template
Transportation Agency for Monterey County Measure X - Senior & Disabled Transportation Program Fiscal Year 2017-18 to 2019-20 PROJECT TIMELINE
| Project Title | [14 empty] | Organization
[6 empty] | Fiscal Year 2017/18 | [11 empty] | FY 2018/19 | [11 empty] | FY 2019/20
Task # | Task | Deliverable | Total Cost | Measure X | Other | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
1
1.1 |  |  | 0
1.2 |  |  | 0
1.3 |  |  | 0
2
2.1 |  |  | 0
2.2 |  |  | 0
2.3 |  |  | 0
2.4 |  |  | 0
3
3.1 |  |  | 0
3.2 |  |  | 0
3.3 |  |  | 0
3.4 |  |  | 0
3.5 |  |  | 0
4
4.1 |  |  | 0
4.2 |  |  | 0
5
5.1 |  |  | 0
5.2 |  |  | 0
5.3 |  |  | 0
6
6.1 |  |  | 0
6.2 |  |  | 0
|  | TOTAL | 0 | 0 | Other: 0

## Sample
Transportation Agency for Monterey County Measure X - Senior & Disabled Transportation Program Fiscal Year 2017-18 to 2019-20 PROJECT TIMELINE
Project Title |  | Senior and Disabled Transportation Service | [13 empty] | Organization | [6 empty] | Non-Profit A
[6 empty] | Fiscal Year 2017/18 | [11 empty] | FY 2018/19 | [11 empty] | FY 2019/20
Task # | Task | Deliverable | Total Cost | Measure X | Other | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
1 | Project Management
1.1 | Project Kickoff meeting | Meeting agenda and meeting minutes | 500 | 500 | bar: Fiscal Year 2017/18 F
1.2 | Project monitoring | Monthly monitoring report | 1500 | 1500
0
2 | Public Outreach
2.1 | Marketing Plan | Marketing plan | 11000 | 3000 | Other: 8000
2.2 | Resource Fair | Agency website, social media pages, staff time | 10000 |  | Other: 10000
2.3 |  |  | 0
3 | Transportation Service
3.1 | Purchase accessible van | Invoice documents | 10000 | 10000 | bar: Fiscal Year 2017/18 A
3.2 | Hire Driver | hiring documents | 10000 | 10000 | bar: Fiscal Year 2017/18 A to Fiscal Year 2017/18 M
3.3 | Begin service | service schedule & service | 50000 |  | Other: 50000
4 | Fiscal Management
4.1 | Quarterly Invoicing | Invoice documents | 1500 |  | Other: 1500
4.2 | Annual Reports | Annual Report | 500 |  | Other: 500
|  | TOTAL | 95000 | 25000 | Other: 70000